## prd-env-task
Project |  | Document | Enviornement |  | By | On
<Project> |  | s3 & Retention | Prd | Create | Onkar | 2025-09-15
|  |  |  | Update | Onkar | 2025-09-19
| Area | Description | Status | Action Owner | ETA | env
[A] | DB Backup Strategy | 1) MySQL backup with 7-day retention, executed daily at 00:00 UTC on server Backup format: dbname_20YY-MM-DD.sql.gz. | ✅ Completed | Pranav | 2025-09-05 | live
|  | 2) Cross s3 Bucket account replication set, region eu-central-1 s3://<Project>-prd-backup --> <Project>-prd-backup-dr | ✅ Completed | Onkar | 2025-09-04 | live
|  | 3) MySQL backup script tranfer to another location & daily run at midnight UTC /etc/rotatelogs/backup/backup_mysql.sh | ✅ Completed | Onkar | 2025-09-17 | live
|  | 4) Replace AWS access key with EC2 IAM Role for S3 access (security best practice). IAM role:- | ✅ Completed | Onkar | 2025-09-18 | live, stg
[B] | Log Management & Backup | 1) Configure daily log rotation (Perl + compression), sync to S3, retain logs locally for 90 days. Includes App, Web, DB, Cron & Security logs. /etc/rotatelogs/rotatelogs.conf | ✅ Completed | Onkar | 2025-09-18 | live, stg
|  | 2) /etc/rotatelogs/log-sync-s3.sh daily at 00:00 UTC sync with s3 bucket | ✅ Completed | Onkar | 2025-09-19 | live
[C] | AWS Cost Optimization | 1) Migration to t3a instance family + purchase of 1-year/3-year Reserved Instances for cost savings. | 🔄 Pending |  | DD-MM-YYYY
|  | 2) degraded ec2 Staging-BT-Backend-Server from t3.medium to t3a.small | ✅ Completed | Onkar. Pranav | 2025-09-19 | stg
[D] | Monitoring | Setup CloudWatch alarms or Xymon monitoring for ec2 services and infrastructure. | 🔄 Pending |  | DD-MM-YYYY
[E] | OS Hardening | 1) Hostname standardization, memory tuning, timezone configuration, OS pkg update etc swap memory added /opt/swap-file 1 GB & free memory script set /etc/rotatelogs/free.sh which run at every 30th minute | ✅ Completed | Onkar | 2025-09-18 | live, stg
|  | 2) OS Timezone UTC is ok, so no change need | No Action | -
[F] | Security Enhancements | 1) Remove global MySQL port access & whitelist sources. | 🔄 Pending |  | DD-MM-YYYY
|  | 2) Configure SSH key-based login per user. Share user mailid who going to access server using ssh key | 🔄 Pending |  | DD-MM-YYYY
|  | 3) Create read-only DB user. DB read user/ Password = readonlyuser / read@25Only | ✅ Completed | Onkar | 2025-09-18 | live
|  | 4) Correct permissions/ownership for document root. | 🔄 Pending |  | DD-MM-YYYY

## Retention
Project |  |  |  |  | Document |  | Enviornement |  |  | By | On
<Project> |  |  |  |  | s3 & Retention |  | Live env |  | Create | Onkar | 2025-09-15
[9 empty] | Update | Onkar | 2025-09-15
|  |  | Src AWS A/c:- | 90347913xxx (src@gmail.com)
|  |  | Region:- | Europe (eu-central-1)- (Frankfurt)
|  |  | bucket name:- | s3://<Project>-prd-backup
|  |  | Dst AWS A/c:- | 39536135xxxx (dst@briota.co)
|  |  | Region:- | Europe (eu-central-1)- (Frankfurt)
|  |  | replica bucket name:- | s3://<Project>-prd-backup-dr
| E.g. | Archiving_Amazon_S3_Data_to_Amazon_Glacier
e.g.
The object was uploaded to the target bucket on Jan 1st 2015. The creation date of this object is Jan 1st 2015.
On October 1th, 275 days after the object’s creation date, the Lifecycle rule takes effect and automatically archives the object to the Glacier Storage Class.
On January 9th, 100 days after the object’s creation date, the Lifecycle rule takes effect again and automatically deletes expires the object.
Since Versioning is suspended on this bucket, the expiration results in the creation of a delete marker with version ID "null".
The object is now permanently deleted and cannot be recovered.
|  |  |  | Uploaded in S3 |  | S3 bucket | Archive in Glacier
|  | Server |  | 1st Jan 2025 |  | Oct 1st 2025 | Oct 1st 2025 | After 720 days archive logs are deleted from Glacier
|  | 90 days log |  | CreationDate |  | 275 days logs | 720 days logs
Glacier : Suitable for archiving data, where data access is infrequent and a retrieval time of several hours is acceptable.
Uses the very low-cost Amazon Glacier storage service, but managed through Amazon S3